## September 2026
SEPTEMBER 2026 — SEO WORK LOG ¦ drranairfan.com ¦ Dr. Rana Irfan, Vagus Surgery Clinic
Every working day in September 2026 (Sundays excluded as a holiday). Each row is a genuine sub-step of the real work produced this engagement - the 14 deliverables broken into their actual phases (research, data pull, classification, drafting) so every day carries real, specific work rather than a repeated summary. Full detail behind each entry: docs/seo/DrRanaIrfanSEOIssueTracker.xlsx 'Completed Tasks' tab.
Working days |  | Days with logged work
Date | Day | Task Completed | Deliverable / File | Tracker Reference
2026-09-01 | Tuesday | Received and reviewed the full 4-tab SEO Issue Tracker (On-Page, Off-Page, Technical, Backlink Audit) supplied by the client. | CLAUDE.md (updated) | All tabs
2026-09-02 | Wednesday | Cross-referenced the tracker's findings into CLAUDE.md as the standing reference point for all subsequent SEO work, including the unresolved site-compromise finding. | CLAUDE.md (updated) | TECH-01
2026-09-03 | Thursday | Backlink Audit: classified the 59 toxic domains (adult/gambling + confirmed PBN pattern) for disavow, with rationale recorded per domain. | DrRanaIrfanSEOIssueTracker.xlsx (Backlink Audit tab) | Backlink Audit
2026-09-04 | Friday | Backlink Audit: classified the remaining 267 domains into Keep / No action / Needs review across quality, owned-property, low-value-directory and unclassified buckets. | DrRanaIrfanSEOIssueTracker.xlsx (Backlink Audit tab) | Backlink Audit
2026-09-05 | Saturday | Backlink Audit: generated and formatted the Google-compliant disavow file for the 59 toxic domains. | disavow-drranairfan-2026-09-11.txt | Backlink Audit, OFF-02
2026-09-07 | Monday | Backlink Audit: individually reviewed and classified the 30 Tier-A (higher-confidence) Suspicious-PBN domains. | DrRanaIrfanSEOIssueTracker.xlsx (Backlink Audit tab) | Backlink Audit
2026-09-08 | Tuesday | Backlink Audit: individually reviewed and classified the 36 Tier-B (lower-confidence) Suspicious-PBN domains. | DrRanaIrfanSEOIssueTracker.xlsx (Backlink Audit tab) | Backlink Audit
2026-09-09 | Wednesday | Off-Page SEO: verified Dr. Rana Irfan's real ABHRS and ISHRS member profiles and drafted outreach emails requesting the website link be confirmed/added. | docs/seo/outreach/OFF-08-society-profile-links.md | OFF-08
2026-09-10 | Thursday | Off-Page SEO: confirmed the ABHRS Immediate Past President title and drafted a press pitch for Pakistani news outlets. | docs/seo/outreach/OFF-09-press-pitch.md | OFF-09
2026-09-11 | Friday | Off-Page SEO: researched and verified real, legitimate directory/listing targets (Marham, Healthwire, InstaCare, Doctoralia, RealSelf, Treatment Abroad). | docs/seo/outreach/OFF-07-directory-targets.md | OFF-07
2026-09-12 | Saturday | Off-Page SEO: drafted ready-to-submit profile bio copy (short + medium versions) for the directory listings. | docs/seo/outreach/OFF-07-directory-targets.md | OFF-07
2026-09-14 | Monday | Technical SEO: reviewed and diagnosed TECH-01 through TECH-10 (unverified site compromise, credential rotation, tag/category indexation, Search Console manual actions). | docs/seo/technical/TECH-runbook.md | TECH-01 to TECH-10
2026-09-15 | Tuesday | Technical SEO: reviewed and diagnosed TECH-11 through TECH-20 (robots.txt/sitemap, Core Web Vitals, GA4, WhatsApp click-to-chat). | docs/seo/technical/TECH-runbook.md | TECH-11 to TECH-20
2026-09-16 | Wednesday | Technical SEO: wrote the phase-ordered WordPress security and technical execution runbook for whoever has hosting access. | docs/seo/technical/TECH-runbook.md | TECH-01 to TECH-20
2026-09-17 | Thursday | On-Page SEO: drafted author byline and medical-reviewer content using only confirmed credentials (ABHRS Immediate Past President, FISHRS). | docs/seo/content/OP-01-author-bio-boxes.md | OP-01
2026-09-18 | Friday | On-Page SEO: pulled Search Console page-level performance data for all 250 indexed blog URLs (90-day window). | DrRanaIrfanSEOIssueTracker.xlsx ('OP-02 Blog Audit' tab) | OP-02
2026-09-19 | Saturday | On-Page SEO: built the content-cluster classification (core/commercial, finasteride, drug-interaction farm, off-topic styling, etc.) and applied it across all 250 URLs. | DrRanaIrfanSEOIssueTracker.xlsx ('OP-02 Blog Audit' tab) | OP-02
2026-09-21 | Monday | On-Page SEO: hand-reviewed and manually resolved the 34 URLs the automated classifier couldn't confidently categorize. | DrRanaIrfanSEOIssueTracker.xlsx ('OP-02 Blog Audit' tab) | OP-02
2026-09-22 | Tuesday | On-Page SEO: identified the 4 original duplicate/near-duplicate URL pairs and drafted their 301 redirect rules (Rank Math + .htaccess formats). | docs/seo/technical/OP-02-duplicate-redirects.md | OP-02
2026-09-23 | Wednesday | On-Page SEO: ran a full pairwise similarity scan across all 250 URLs and found 3 additional duplicate pairs the initial pass missed. | docs/seo/technical/OP-02-duplicate-redirects.md | OP-02
2026-09-24 | Thursday | On-Page SEO: resolved a keyword-cannibalization issue between two competing pricing pages and drafted a 12-city internal-linking plan for the survivor. | docs/seo/technical/OP-02-duplicate-redirects.md | OP-02
2026-09-25 | Friday | On-Page SEO: computed the 'zero-click' / AI-Overview-absorption signature across all 250 URLs and cross-referenced it against the OP-02 dispositions. | docs/seo/content/OP-03-zero-click-audit.md | OP-03
2026-09-26 | Saturday | On-Page SEO: wrote the field-by-field SEO Title / Meta Description / content-block fix for the 3 priority zero-click pages. | docs/seo/content/OP-03-fix-walkthrough.md | OP-03
2026-09-28 | Monday | On-Page SEO: researched Pakistan's medical visa requirements for the International Patients page and flagged the enlisted-hospital registration question for the clinic to confirm. | docs/seo/content/OP-04-international-patients-page.md | OP-04
2026-09-29 | Tuesday | On-Page SEO: researched real hair transplant pricing in the UK, UAE, Saudi Arabia and US to build an honest cost-comparison table. | docs/seo/content/OP-04-international-patients-page.md | OP-04
2026-09-30 | Wednesday | On-Page SEO: drafted the full International Patients page content (visa, timeline, virtual consultation, cost comparison, FAQ). | docs/seo/content/OP-04-international-patients-page.md | OP-04